## Project Github
Name | Github
林志鴻 / John
伍恒康 / Allen
詹淳凱 / Chun-Kai
陳伊均 / Chen I-Chun
林彤珊 / Angela Lin
黃紹航 / Steven Huang
羅翊栩 / Yi Hsu Lo | https://github.com/yihsu-lo/Project-2.git
施蘊庭 / Erin
于謹嘉 / Yu Chin Chia | https://github.com/ji3g4m6zo6/mMessenger
蔡漢聲 / Hank | https://github.com/HankMountain/OrienteeringCITY
張宜群 / I-CHUN CHANG | https://github.com/michaelrevlis/Project2-TRUEST.git
王迺瑜 / Wang Nai Yu
莊愉萱 / Rosalie
許雅筑 / Noelle

## Template
User Story |  | Page | Module | Module | Functions | Task | Working days | To | Doing | Done
1 | As an user, I want to track my riding path so open the App | Loading Page |  | Data system | Query Data from data TP | Load youbike info from data TP | 3 Days
2 | I want to track my path, so I can click the begin button | Home Page | Tracking System |  |  | Load bike route from data TP | 3 Days
2.1 | I want to know how much distance I already rode, so I can see the distance |  | Record System |  |  | Load rental spot info | 2 Days
2.2 | I want to know current weather, so I can see the weather informaiton |  | Data System |  |  | Load 休息站 info
2.3 | I want to know current air quality (pm2.5), so I can see the air quality information |  | Data System |  | Weather System | Query Current weather
3 | To track my path, I need a tracking page | Tracking page |  |  |  | Query Air polution Info
3.1 | I need to record how much time I have ridden (time) |  | Tracking System
3.2 | I need to record how long I have ridden (distance) |  | Tracking System | Record System | Store a record | Get data from device | 4 Days
3.3 | I need to record the current speed (speed) |  | Tracking System |  |  | Record Total Distance
3.4 | I need to take a break, so I can click the pause button |  | Tracking System |  |  | Record Calories
3.5 | I want to continue ride, so I can click the resume button |  | Tracking System |  |  | Record total Time
3.6 | I want to finish this ride, so I can click the finish button |  | Tracking System |  |  | Record avg Speed
4 | I want to know the result, so I need to open my analysis page | Result page |  |  |  | Record overall Route
4.1 | I want to know how much cal I consumed, so I need to caculate cal |  | Record System | Tracking System | Calculate | Calculate spontaneous distance
4.2 | I want to know how long I rode, so I can see the distance |  |  |  |  | Calculate spontaneous Calories comsuption
4.3 | I want to know the total time, so I can see the time |  |  |  |  | Calculate spontaneous Total Time
4.4 | I want to know my average speed, so I need to get my time and speed |  |  |  |  | Calculate spontaneous Speed
4.5 | I want to see my routes and map, so I need to add google map in it plus start and destination |  |  |  |  | Record spontaneous route
4.6 | I want to share my record, so I need to click the share button ( optional) |  |  |  | Actions | Pause
4.7 | I want to share my record, so I need to log in my facebook account (optional) |  |  |  |  | Resume
5 | I want to know monthly statistic, so I need to see the total information | History page |  |  |  | Stop

## Hank
User Story |  | Page | Module | 優先順序 | Module | Functions | Task | Working days
1 | As an user, I want to play the OrienteeringCity, so I open the App | Loading Page |  | 1 | Tracking
2 | I want the login with facebook, and store my login detail. So I click the login Button | Login Page |  | 2
3 | I want to use the OrienteeringCity App, so I look up the main page | Main Page |  | 3
4 | I want to check today`s event, so I click Todat`s Event button | Today`s event Page |  | 4
4.1 | I need to know today`s event start location |  |  | 5
4.2 | I need to know today`s event description |  |  | 6
4.3 | I need to know today`s event count down time |  |  | 7
4.4 | I need to start today`s event , so I click the Start Button
5 | I need to start today`s event , so I look up the Running Page with 2 map | Running with 2 map Page |  |  | Recording
5.1 | I need to checkin in fisrt point, so I click the checkin button
5.2 | I need to know where I am now.(map)
5.3 | I need to know next destination point.(map)
5.4 | I need to know final destination point.(map)
5.5 | I need to know my route from begin.(map)
5.6 | I need to know the time I spend from begin.
5.7 | I need to know how many check point I finished. |  |  |  | Data
5.8 | I need to know how many check point I left.
5.9 | I need to know how long I run from begin.
5.10. | I need to know whether I checkin now.
5.11 | I need to know the distance from my current location to the next check point.
5.12 | I want to stop running event, so I click stop button |  |  |  | Camera
6 | I want to play the event with compass and map, so I click the button to Running Page with Compass | Running with Compass Page
Detail same as Running Page with 2 map
7 | I want to check in with QR code, so I click the QR code Page Button | QR Code Scan Page
7.1 | I want to scan QR code, so I click scan button.
7.2 | I want to scan QR code, so open the camera.
8 | I want to check History Event`s, so I look up the History Event`s page | History Event`s Page
8.1 | I want to check History Event`s detail, so I click the cell.
9 | I want to check History Event`s detail, so I look up the History Event`s Detail Page | History Event`s Detail Page
10 | I want to check the Upcoming Event, so I look up the Upcoming Event Page | Upcoming Event Page
10.1 | I need to know Upcoming event`s start location
10.2 | I need to know Upcoming event`s description
10.3 | I need to know Upcoming event`s count down time
11 | I want to look my personal Profile, so I look up the Personal Profile Page | Personal Profile Page
11.1 | I want to edit my personal Profile, so I look click the edit button
11.2 | I want to edit my profile picture.
11.3 | I want to edit my profile name
11.4 | I want to edit my profile description

## Jia
User Story |  | Page | Module | Module | Functions | Task | Working days | To | Doing | Done
1 | 希望能透過 App 以氣泡訊息的形式收法Gmail信件 | Loading Page |  | Gmail SDK | Query Data from Gmail API | 從API提取信件 | 1 Day
1.1 | 我希望以Gamil登入 | Gamil Login Page | Gmail SDK |  |  | 從API寄信 | 0.5 Day
1.2 | 我希望讀取速度能加快，不要每次進入App都要等很久 | Home Page | 收件系統 |  |  | 從API提取通訊錄名單 | 0.5 Day
2 | 我希望可以在首頁看到最新收到的訊息，以寄件者排列 |  |  | 收件系統 | 儲存至Core Data，從CoreData提取，資料排列 | 將所有資料儲存至Core Data | 0.5 Day
2.1 | 我希望可以在首頁看到 寄件者，寄件標題，訊息預覽，寄件者頭像 |  |  |  |  | 將資料從Core Data提取出來並且按照指定排列 | 0.5 Day
3 | 我希望點寄件者之後，能進入第二頁面，以收件時間排列信件 | Second receive mail Page |  |  |  | 將信件系統增加搜尋功能 | 1 Day
4 | 我希望進入信件之後，能以氣泡式訊息呈現 | Message Page | 訊息系統 | 訊息系統 | 透過訊息系統顯示與發送資料 | 套用第三方Message SDK | 0.5 Day
4.1 | 我希望能按下發送即寄信 |  |  |  |  | 調整訊息系統UI | 0.5 Day
5 | 我希望通訊錄系統能獲得我Gamil的聯絡名單 | 通訊錄頁面 | 通訊錄系統 |  |  | 使用發送按鈕傳送Mail | 1 Day
5.1 | 我希望通訊錄系統能以姓名筆畫排列 |  |  | 通訊錄系統 | 通訊錄能從 Gmail拿到資料，新增與刪除資料 | 創建通訊錄Core data | 1 Day
5.2 | 我希望通訊錄能顯示最近交談的五位對象，並顯示在Tableview前五個Cell |  |  |  |  | 將通訊錄資料存到 Core data | 0.5 Day
5.3 | 我希望通訊錄能新增收件者 |  |  |  |  | 新增使用者資料到Core Data | 0.5 Day
5.4 | 我希望通訊錄能透過滑動刪除收件者 |  |  |  |  | 從Cell刪除資料 同時移除Core Data資料 | 0.5 Day
6 | 我希望能透過手勢滑開側邊選單 | Side Navigation Menu |  |  |  | 修改發送系統，可以使用通訊錄的資料 | 1 Day
6.1 | 我希望側邊選能顯示Mail Address和 User name |  | Gmail SDK |  |  | 透過使用者名稱排列通訊錄 | 0.5 Day
6.2 | 我希望側邊選單能有登出功能 |  |  |  |  | 在通訊錄增加搜尋功能 | 0.5 Day
到時若想到有更多功能可以再補上，或者有卡關也有多餘時間可以利用

## Yi Hsu
User Story |  | Page | Module | Functions | Task | Working days | To | Doing | Done
1 | User want to buy and sale cars | Landing Page |  |  |  | 1
2 | User can buy the cars | Home Page |  |  |  | 1
2.1 | User can sale the cars | Home Page
2.2 | User can check their previous saved items | Home Page
3 | User can find the cars with different criteria (brand, area, price…etc.) | Buy Page | Data |  | Search | 3
4 | User can get the search result | Search Result Page | Data
5 | User can check the detail information of the vehicle | Buy Detail Page | Data
5.1 | User can save the cars they are interested in | Buy Detail Page | Data
5.2 | User can send messages to the owner (Facebook) | Buy Detail Page | Facebook SDK |  |  | 1
5.3 | User can rate the owner (after messenger been dismissed?) | Buy Detail Page |  |  |  | 1
5.4 | User can get the estimated tax information | Buy Detail Page |  | Calculate
6 | User can upload their cars for sale | Sale Page |  |  | Store | 3
6.1 | User can confirm the information before issuing | Sale Detail Page
6.2 | User can edit and delete their vehicle | Sale Detail Page | Data |  |  | 1
7 | User can check their own Facebook page | Mine Tab Bar Page | Facebook SDK
7.1 | User can check their own rating | Mine Tab Bar Page
7.2 | User can check their selling items | Mine Tab Bar Page |  |  | Store | 1
7.3 | User can check the items they are interested in | Mine Tab Bar Page |  |  | Store

## Rosalie
User Story | Page | Module | Module | Functions | Task | Working days | To | Doing | Done